## Events
Events
2008-10-25 | C130, TO and G1 flew today. We are still waiting for pylons
2008-10-26 | VA01 test flight along 20° S to 74° 38' W
2008-10-27 | Waiting for Thomas and co. to get passes
2008-10-28 | VA02 test flight for polarimeter.
2008-10-29 | Waited all day for pylons. Finally arrived 6.00. All equipment fitted, also E+H disks replaced
2008-10-30 | VA03 flight over Ron Brown coord with 146. Aimms recorded position not met
2008-10-31 | VA04 20°S mission with C130 below, 146 above. Cloud broken
2008-11-01 | Hugo and Phil worked on lidar, improving its signal
2008-11-02 | VA05 stand-alone mission to measure free tropospheric aerosol with a succession of profiles.
2008-11-03 | VA06 coordinated with 146: flew to Peruvian border then towards 75W 20S with 146 below; retraced track
2008-11-04 | VA07 20S mission with all five airplanes, out to 76W at 15000 back at 11000 and 10000
2008-11-05 | VA08 pollution proifiling along coast. Sebastian arrived in the evening
2008-11-06 | Sebastian fixes lidar. VA09 test flight ot to alpha at 15000'
2008-11-07 | All hands meeting in morning
2008-11-08 | Down day. Keith, Jonny and Hugh repair PCASP
2008-11-09 | VA10, started late because of problems with engine. 20 S mission.
2008-11-10 | VA11, flying down south in search of pollution. None found except very near Arica
2008-11-11 | Down day due to no pollution and nobody else flying
2008-11-12 | Aborted flight VA12 due to electrical problems
2008-11-13 | Two flights: VA13 low-level intercomparison with 146; VA14 20°S
2008-11-14 | VA15: aerosol profiling mission out to 72 W
2008-11-15 | end of VOCALS

## Do flight
Dornier flights |  |  | Alpha=72°W, 20°S
| Flight | Science | Duration | Take | Land | Mission |  | Flight plan
|  | Plan | hours | off |  | Scientists
|  |  |  | LT | LT
2008-10-25
2008-10-26 | VA01 | test | 3.1833 | 11:16 | 14:27 | GV | HR | to Alpha then west to 74° 38' W at 15000'
2008-10-27
2008-10-28 | VA02 | test | 1.6833 | 9:49 | 11:30 | HR | TR | to alpha at 15000', circle descent to 10000' then return
2008-10-29
2008-10-30 | VA03 | Ron Brown | 4.1667 | 8:38 | 12:48 | HR | LL | to RB at 19° 35.5' S, 74° 46.9' W, then four transects along 150°/330° away from RB to SE
2008-10-31 | VA04 | 20°S | 3.9333 | 8:30 | 12:26 | GV | LL | to alpha at 15000', then west to 76°W, back along same track
2008-11-01
2008-11-02 | VA05 | Profiling | 3.2833 | 8:54 | 12:11 | GV | AH | Flew towards 19.5 S 20 W, profiling cloud top-15000'. Spiral descent included
2008-11-03 | VA06 | Pollution | 3.6 | 10:00 | 13:36 | LL | HR | Flew to Peruvian border then followed coordinated track with 146 towards DART
2008-11-04 | VA07 | 20°S | 4.2 | 8:31 | 12:43 | GV | LL | to alpha then 76°W at 15000'; return at 11000' then 10000'
2008-11-05 | VA08 | Profiling S | 3.1833 | 10:00 | 13:11 | GV | LL | Pollution profiling along the coast to 22°39' S, 71° 10' W
2008-11-06 | VA09 | Lidar test | 1.65 | 15:35 | 17:14 | HR | SD | Lidar test flight to pt alpha at 10-15,000 ft
2008-11-07
2008-11-08
2008-11-09 | VA10 | 20°S | 4.2167 | 10:39 | 14:52 | LL | HR | 20°S flight with 146
2008-11-10 | VA11 | Pollution | 4 | 8:23 | 12:23 | GV | AH | Flight to the south of Arica at 15000'. Overpass of 146
2008-11-11
2008-11-12 | VA12 | Ron Brown | 0.73333 | 8:35 | 9:19 | LL | HR | Flight aborted because of fault on inverters.
2008-11-13 | VA13 | Intercomparison | 1.6667 | 7:05 | 8:45 | LL | - | Intercomparison at low level with 146
2008-11-13 | VA14 | 20°S | 4.05 | 9:45 | 13:48 | GV | JvB | 20°S mission overflying C130, underflying 146
2008-11-14 | VA15 | Profiling S | 3.6 | 10:15 | 13:51 | HR | LL | Aerosol profiling west and south of Arica
total hrs |  |  | 47.15
GV | Geraint Vaughan | [5 empty] | TR | Thomas Ruhtz | JvB | Jonas von Bismarck
HR | Hugo Ricketts | [5 empty] | AH | Andre Hollstein
LL | Lorenzo Labrador | [5 empty] | SD | Sebastien Dubois

## Do Equipment
Dornier instrument status
n: not flown, x: not working, p: part working, y: working
Flight
| AIMMS | E+H | LIDAR | PCASP | FSSP | Grimm | APPLANIX | UV | AMSSP
2008-10-25
2008-10-26 | n | p | p | n | n | y | y | y | n | VA01
2008-10-27
2008-10-28 | n | p | p | n | n | y | y | y | y | VA02
2008-10-29 | [10 empty] | pylons fitted
2008-10-30 | p | y | p | p | y | y | y | y | y | VA03 | position only from AIMMS, no met data
2008-10-31 | y | y | p | p | y | y | y | y | y | VA04
2008-11-01 | [10 empty] | lidar improved
2008-11-02 | y | y | p | p | y | y | y | y | y | VA05
2008-11-03 | y | y | p | p | y | y | y | y | y | VA06
2008-11-04 | y | y | p | p | y | y | y | y | y | VA07
2008-11-05 | y | y | p | p | y | y | y | y | y | VA08
2008-11-06 | y | y | y | p | y | y | y | y | n | VA09 | lidar repaired
2008-11-07
2008-11-08 | [10 empty] | PCASP repaired
2008-11-09 | y | y | y | y | y | y | y | y | y | VA10
2008-11-10 | y | y | y | y | y | y | y | y | y | VA11
2008-11-11
2008-11-12 | y | y | y | y | y | y | y | y | y | VA12
2008-11-13 | y | n | n | y | y | y | y | n | n | VA13 | remote sensing not operated
2008-11-13 | y | y | y | y | y | y | y | y | y | VA14
2008-11-14 | y | y | y | y | y | y | y | y | y | VA15
Eagle data not recorded at full resolution for first two flights
Lidar recorded only cloud top for first 4 flights, then low quality aerosol plus cloud top till 6 Nov
PCASP suffered from erroneously high counts in first few channels. On 8 Nov it was found
to have loose fittings so data before then are suspect.
VA13 was low-level only for probe intercomparison with 146

## Sheet1
|  |  | Take off | Land | Duration
|  |  | UT | UT | hours
2008-10-26 | VA01 | test | 14:16 | 17:27 | 3:11 | 3:00
2008-10-27
2008-10-28 | VA02 | test | 12:49 | 14:30 | 1:41
2008-10-29
2008-10-30 | VA03 | Ron Brown overflight | 11:38 | 15:48 | 4:10
2008-10-31 | VA04 | 20°S | 11:30 | 15:26 | 3:56
2008-11-01
2008-11-02 | VA05 | Profiling | 11:54 | 15:11 | 3:17
2008-11-03 | VA06 | Pollution gradient | 13:00 | 16:36 | 3:36
2008-11-04 | VA07 | 20°S | 11:31 | 15:43 | 4:12
2008-11-05 | VA08 | Profiling S | 13:00 | 16:11 | 3:11
2008-11-06 | VA09 | Lidar test | 18:35 | 20:14 | 1:39
2008-11-07
2008-11-08
2008-11-09 | VA10 | 20°S | 13:39 | 17:52 | 4:13
2008-11-10 | VA11 | Pollution gradient | 11:23 | 15:23 | 4:00
2008-11-11
2008-11-12 | VA12 | Ron Brown | 11:35 | 12:19 | 0:44
2008-11-13 | VA13 | 146 intercomparison | 10:05 | 11:45 | 1:40
2008-11-13 | VA14 | 20°S | 12:45 | 16:48 | 4:03
2008-11-14 | VA15 | Profiling S | 13:15 | 16:51 | 3:36
Test flights
High-level (15000') remote sensing flights, usually with other aircraft beneath
Aerosol profiling flights, between cloud top and 15000'
Intercomparison of wing probes with 146 at low level